## Sheet1
KEY | Work Day | Finish day | Hard Stop Date | Mechanical work completed
DATE | SAT | SUN | MON | TUES | WED | THURS | FRI | SAT | SUN | MON | TUES | WED | THURS | FRI | SAT | SUN | MON | TUES | WED | THURS | FRI | SAT | SUN | MON | TUES | WED | THURS | FRI | SAT | SUN | MON | TUES | WED | THURS | FRI | SAT | SUN | MON | TUES | WED | THURS | FRI | SAT | SUN | MON | TUES | WED | THURS | FRI | SAT | SUN | MON | TUES | WED | THURS | FRI | SAT | SUN | MON | TUES | WED | THURS | FRI | SAT | SUN
 | time axis 2020-01-04 to 2020-03-08
WEEK | 2020-01-04: WEEK 1; 2020-01-12: WEEK 2; 2020-01-19: WEEK 3; 2020-01-26: WEEK 4; 2020-02-02: WEEK 5; 2020-02-09: WEEK 6; 2020-02-16: WEEK 7; 2020-02-23: WEEK 8; 2020-03-01: WEEK 9; 2020-03-08: WEEK 10
Meeting/Work Schedule | 2020-08-04 | X | 3:30-6 | 3:30-6 | 3:30-6 | X | X | 2020-10-04 | X | 3:30-6 | 3:30-6 | 3:30-6 | X | 3:30-5 | 2020-10-04 | X | 2020-10-04 | 3:30-6 | 3:30-6 | X | X | X | X | 3:30-6 | 3:30-6 | 3:30-6 | X | X | 2020-10-04 | X | 3:30-6 | 3:30-6 | X | X | X | X | X | X | 3:30-6 | 3:30-6 | 3:30-6 | 3:30-6 | 2020-10-04 | X | 3:30-6 | 3:30-6 | 3:30-6 | X | X | 2020-10-04 | X | 3:30-6 | 3:30-6 | 3:30-6 | X | X | X | X | 3:30-6 | 3:30-6 | 3:30-6 | X | X | X | X
Objective:
Kickoff | bar: 2020-01-04
Brainstorming | bar: 2020-01-04; 2020-01-06 to 2020-01-08
Top 10 designs | bar: 2020-01-06 to 2020-01-08
Evaluate/Eliminate designs | bar: 2020-01-06 to 2020-01-10
Test Kit and Data Collection | bar: 2020-01-06 to 2020-01-08
Design Related Component | bar: 2020-01-04; 2020-01-06 to 2020-01-08
Strategy Related Component | bar: 2020-01-04; 2020-01-06 to 2020-01-11; 2020-01-13
Design Finalized (Drive) | bar: 2020-01-08 to 2020-01-11; 2020-01-13
Order/Build (Drive) | bar: 2020-01-13 to 2020-01-25; 2020-01-27
Primary Mechanism Prototyping | bar: 2020-01-07 to 2020-01-11; 2020-01-13 to 2020-01-16
Primary Mechanism Engineering | bar: 2020-01-11; 2020-01-13 to 2020-01-18; 2020-01-20
Order/Build ( Primary Mechanism ) | bar: 2020-01-17 to 2020-01-18; 2020-01-20 to 2020-01-25; 2020-01-27 to 2020-01-31
Secondary Mechanism Prototype | bar: 2020-01-07 to 2020-01-11; 2020-01-13 to 2020-01-16
Secondary Mechanism Engineer | bar: 2020-01-11; 2020-01-13 to 2020-01-18; 2020-01-20
Order/Build (Secondary Mechanism) | bar: 2020-01-17 to 2020-01-18; 2020-01-20 to 2020-01-25; 2020-01-27 to 2020-01-31
Final Mechanical Assembly | bar: 2020-01-28 to 2020-02-01; 2020-02-03 to 2020-02-07
Electrical Board Design | bar: 2020-01-17 to 2020-01-24
Pneumatic Schematic | bar: 2020-01-17 to 2020-01-24
Electrical Board Construction | bar: 2020-01-24 to 2020-01-31
Pneumatic Fabrication | bar: 2020-01-24 to 2020-01-31
Bot Wiring | bar: 2020-01-30 to 2020-02-07
Bot Plumbing | bar: 2020-01-30 to 2020-02-07
Programming Test Bed | bar: 2020-01-10 to 2020-01-31
Autonomous Design/Testing | bar: 2020-01-28 to 2020-02-07; 2020-02-10 to 2020-02-15
Programming | bar: 2020-01-28 to 2020-02-07; 2020-02-10 to 2020-02-15
Practice | bar: 2020-02-04 to 2020-02-07; 2020-02-10 to 2020-02-15; 2020-02-17
Shake down | bar: 2020-02-14; 2020-02-16 to 2020-02-17
Robot Crating/Ship | bar: 2020-02-17
Misc.
Driver Station | bar: 2020-01-18 to 2020-01-31
Crate Construction | bar: 2020-01-15 to 2020-01-29
Aesthetics | bar: 2020-01-29 to 2020-02-07